# The 8-week release checklist

A free, printable week-by-week checklist for releasing a single as an independent artist in India, from master and metadata to pitching, content, release day and the four weeks after.

Release date (a Friday): ____________________ Song: ____________________

## Week −8: finish the music

☐  Final master approved (and a clean or radio edit if needed)

☐  Title locked, spelled exactly as it will appear everywhere

☐  Split sheet signed by every writer

☐  Samples cleared, if any

☐  AI use noted, if any, for your distributor's declaration

## Week −7: visuals and story

☐  Cover art, 3000 × 3000 px, no logos or text that break store rules

☐  Press photos, horizontal and vertical

☐  The story of the song in one paragraph

☐  Lyrics typed and checked

## Week −6: metadata and rights

☐  Metadata and credits sheet complete

☐  ISRC assigned (by your distributor, or your own)

☐  Song registered with IPRS by every writer, with matching shares

☐  Release date chosen

## Week −6 to −4: deliver

☐  Uploaded to distributor, all platforms selected

☐  YouTube Content ID and Official Artist Channel requested, if available

☐  Delivery confirmed and no errors flagged

## Week −4: pitch

☐  Song visible under Music → Upcoming in Spotify for Artists

☐  Spotify pitch submitted with accurate genre, mood, language and story

☐  Asked distributor about pitching other platforms

## Week −4 to −1: build anticipation

☐  Content plan written: story, hook, making-of, countdown

☐  Hook clips tested with Trial Reels

☐  Pre-save link live and in your bio

☐  Closest fans told personally (DMs, WhatsApp, email list)

## Week −2: outreach

☐  Personal pitches sent to playlist curators, journalists, blogs and radio

☐  Premiere offered to one outlet, if relevant

☐  EPK updated

## Week −1: final prep

☐  Spotify Canvas uploaded

☐  Music video, lyric video or visualiser scheduled as a YouTube premiere

☐  Release-day posts and stories ready

☐  Link hub updated to go live on release day

## Release day

☐  Song live on all platforms (check each one)

☐  Posts on Instagram, YouTube and everywhere else

☐  Artist Pick and bios updated

☐  Reply to every comment and message

☐  Thank and share everyone who supports it

## Weeks +1 to +4: keep it alive

☐  A new clip of the song every two or three days

☐  Fan videos and playlist adds shared

☐  Numbers checked weekly: active listeners, saves, sends, watch time

☐  Plan an alternative version (acoustic, live, remix) for weeks +4 to +8

☐  Notes written: what worked, what to change next time

Online version and more free documents: surandsauda.in/learn/release-checklist/